## Deliverables
DVM Fire Division — UtilizeCore Deliverables
Go-Live Date: August 1, 2026 |  |  | Last Updated: July 13, 2026
# | Deliverable | Owner | Status | Notes | Due
1 | Companywide filter template for FLS (work orders only) |  | Complete
2 | Get clients from Silpa | Silpa | Pending
3 | Get sites from Anthony | Anthony Pasquarella | Pending
4 | Create scheduled services for all quarterly services |  | Pending
5 | Add DVM Fire's rates |  | Pending
6 | Track inventory |  | Pending
7 | Track employee hours |  | Pending | Separate WOs for PTO, Holiday, Sick; regular hours via UC check-in & check-out
8 | Create a dummy reactive work order to show Silpa | Silpa | Pending | Demo/training reactive WO
9 | Create a dummy PM work order for Silpa | Silpa | Pending | Preventive Maintenance WO demo
10 | Reach out to Frank Trotta re: payroll dashboards | Frank Trotta | Complete | Find out what UC dashboards & reports he uses to track payroll